Assignment 6.1

1. How do you evaluate the performance of a project in agile?
Ans: Performance of a project in agile can be evaluated based on the following factors:
Velocity : It is the measure of the number of user stories deliver after every sprint.
It can be the predicted velocity which is measured based on the previous project data and also can be the actual velocity which is used for the subsequent tasks in release plan.

Hit Rate : It is the measure of amount of work completed from the total allocated work in terms of percentage.

- Work Remaining on Task : It is the amount of work remaining on each currently active/ongoing task. This estimation can be done during daily meetings.
- Project Cost : It is the measure of the actual cost of the project against the planned or estimated cost of the project and generally represented by Cost Performance Index(CPI). If the project is completed within the planned budget then we can say the performance is good and if we the actual cost of the project exceeds the planned budget then the performance is not that good.

- Scheduled Performance Index (SPI) : It measures the performation of the project in terms of time like whether the project has completed within the estimated time or it is extended. It is measured in the numerical digits and the ideal performance of the project is when the value of SPI is 1.
- Earned Business Value (EBV) : EBV is the outcome of the project which means the customer is getting what is really required for him in business growth perspective. The output is the entire project as a whole but the EBV is the key feature of the project which is responsible and important in terms of adding business value.

2. Compare traditional monitoring & control with agile monitoring & control with respect to metrics generation.
Ans:
Traditional	Agile
Focus is on tracking the amount of efforts put on each task	Focus is on tracking the number of user stories delivered (velocity)
Output is given more importance	Outcome is given more importance
Day to day monitoring and meetings are not part of this approach	Daily stand up meetings held to monitor/review the current progress
Following the plan is more important and any chnage from plan is not easily accepted	Accepting the variance is the part of this approach
Monitoring the project is not efficient as team may be scattered to multiple locations	Monitoring the project is easy as the entire team is colocated

3. With a total project budget of $ 175,000, and having completed one out of four Iterations, we have this product backlog and these actuals:
Feature	Estimate / (storypoints)	Completed / (storypoints)	Actual Cost (1000s dollars)
Welcome Screen	10	10	15
Advert - Splash Screen	20	20	30
Login Screen	10	10	20
Personalized Google Ads	20
Catalog Browser	20
Catalog Editor	10
Shopping Basket Browser	5
Shopping Card Editor	25
Check-out Process	20
Invoice Calculation	10
Credit Card Verification	10
PayPal Payment Handling	20
Order Confirmation Email	20
Totals	200	40	65

in our example, after Iteration 1 we should be at 25% complete)
- Calculate Planned Value
- Actual % Complete
- Earned Value

Ans: Given,
Total Project Budget = $ 175,000
Expected amount of work completed after first iteration = 25%
Planned Value = BAC (Budget at complete) * Planned % of work completion
= $175,000 * 0.25
= $ 43,750

Actual % Complete = StoryPoints Completed/ Total Estimated StoryPoints
        = (40/200)*100
        = 20%

Earned Value = BAC (Budget at complete) * Actual % of work completion
      = $175,000 * 0.20
= $ 35,000